## Deliverables and Links
Deliverables | Link
Feature List | ToolShop Demo Features List_Anjitha G Sunil
Test Plan | Tool Shop Demo_Test Plan_Anjitha G Sunil
RTM, Test Case and TE Report | RTM, TE Summary & Test Case_ToolShop Demo_Anjitha G Sunil
Test Summary | Tool Shop Demo_Test Summary_Anjitha G Sunil

## Defect Summary
Defect Summary Report
Total Number of Bugs | Test cases executed | Closed Bugs | Deffered Bugs | Reopened | To Do | In progress /Under development | QA Verification
7 | 69 | 0 | 0 | 0 | 7 | 0 | 0

## Defect Report
Tool Shop Demo - Bug Report
Bug ID | Test case Id | Bug Title | Bug Description | Step to Reproduce | Test Data | Expected Result | Actual Result | Priority | Severity | Visual proof | Issue Type | Envionment | Platform | Device | Assignee | Status | Comments | Verified By
DEF_01 | HP_08 | Price Range Slider | Min slider handle is at absolute minimum catalog proce but Max slider is not at maximum catalog price | 1. Navigate to Home Page 2. Observe initial price slider state. |  | Min slider handle must be at absolute minimum catalog price and Max slider handle must be at absolute maximum catalog price | Min slider handle is at absolute minimum catalog proce but Max slider is not at maximum catalog price | High | High | DEF_01.png | Bug | Staging | Windows 11 | Asus | Developer | Open |  | Anjitha G Sunil
DEF_02 | HP_09 | Price Range Slider | 1. Min handle can be dragged past the Max handle 2. Max handle can be dragged below the Min handle position | 1. Attempt to drag Min handle past the current Max handle position. 2. Attempt to drag Max handle below the current Min handle position. |  | 1. Min handle must be constrained and should not exceed Max handle value. 2. Max handle should not drop below Min handle value. | 1. Min handle can be dragged past the Max handle 2. Max handle can be dragged below the Min handle position | High | High | DEF_02.mp4 | Bug | Staging | Windows 11 | Asus | Developer | Open |  | Anjitha G Sunil
DEF_03 | HP_13 | Pagination | 1. Product grid updates to show Page 2 products 2. Active page indicator updates to "2" 3. Page does not scrolls back to the top of the product grid | 1. Navigate to url 2. Scroll down 3. Click page "2" or "Next" button. |  | 1. Product grid must update to show the Page 2 products. 2. Active page indicator updates to "2". 3. Page scrolls smoothly back to the top of the product grid. | 1. Product grid updates to show Page 2 products 2. Active page indicator updates to "2" 3. Page does not scrolls back to the top of the product grid | High | High | DEF_03.mp4 | Bug | Staging | Windows 11 | Asus | Developer | Open |  | Anjitha G Sunil
DEF_04 | SS_12 | Invalid email format | No warning message is displayed and was able to register with invalid email format | 1. Navigate to url 2. Click Sign in 3. Click Register your account 4. Fill the registration form with an invalid email id | Email: anjitah.com@gmail.com | "E-mail format is invalid" warning message should be displayed | No warning message is displayed and was able to register with invalid email format | High | High | DEF_04.mp4 | Bug | Staging | Windows 11 | Asus | Developer | Open |  | Anjitha G Sunil
DEF_05 | CP_08 | File format specification | No error or warning message is displayed | 1. Navigate to url 2. Click Contact link 3. Fill the form 4. Attach jpg file 5. Click Send |  | Error message or warning message should be displayed on uploading a file in different format | No error or warning message is displayed | High | High | DEF_05.mp4 | Bug | Staging | Windows 11 | Asus | Developer | Open |  | Anjitha G Sunil
DEF_06 | CO_08 | Masked credit card input and CVV protection | CVV and card details are exposed in plain text and not masked | 1. Navigate to url 2. Click a product card 3. Click "Add to cart" button 4. Click cart icon at the top 5. Click proceed to check out till we reach step 3 6. Enter the details 7. Click proceed to check out 8. Click on the "Choose your payment method" drop down 9. Select Credit card 10. Enter card details |  | CVV input characters should be masked and full card credentials should not exposed | CVV and card details are exposed in plain text and not masked | High | Critical | DEF_06.mp4 | Bug | Staging | Windows 11 | Asus | Developer | Open |  | Anjitha G Sunil
DEF_07 | CO_10 | Quantity Controls | Application allows to complete the transaction and no error message is displayed when the quantity is set to zero | 1. Add an item to cart 2. Click cart icon 3. Set quantity to 0 in step 1 4. Click proceed to check out |  | User must not be able to complete the transaction when the quantity is set to zero | Application allows to complete the transaction and no error message is displayed when the quantity is set to zero | High | Critical | DEF_07.mp4 | Bug | Staging | Windows 12 | Asus | Developer | Open |  | Anjitha G Sunil